## 2025
APPENDIX ON TRACK WORK TO THE NETWORK STATEMENT
Location | Year of implementation | Line section | Account line section number | Required infrastructure capacity | Timing of infrastructure capacity requirement | Speed limit | Priority: 1: Implementation decision made 2: Implementation decision will be made later | Annual plan number
Repairs of Töölönlahti railway bridge | 2025 | Helsinki–(Pasila) | 1101 | Will be specified as planning proceeds | Will be specified as planning proceeds | Will be specified as planning proceeds | 2 | -
Kehä III (Main Road 50/Ala-Tikkurilantie) bridge repair | 2025 | (Pasila)–(Riihimäki) | 1102 | Will be specified as planning proceeds. | - | 50 and 80 km/h | 1 | -
Renewal of turnouts on Hanala’s western tracks and axle track alterations | 2025 | (Pasila)–(Riihimäki) | 1102 | Will be specified as planning proceeds, probably at least a 24-hour Midsummer service break and speed limits 50/80 after the work for a few weeks. | Will be specified as planning proceeds. Probably a Midsummer service break or similar. | 50/80 for a few weeks after the work and retamping | 2 | -
Leppävaara–Espoo: Espoo City Line (ESKA) | 2025 | (Pasila)–Kirkkonummi | 1104 | Traffic arrangements on line section (Leppävaara)–Kauklahti April–May: 4–6 full service breaks, each lasting 12 hours. Full service breaks from Midsummer. duration 5 weeks. September–October. 4–6 full service breaks during weekends, duration 12 h. | 1 April –31 October | 50 and 80 km/h | 1 | -
Renovation of Malminkartano tunnel | 2025 | (Huopalahti)–Vantaankoski–Havukoski | 1105 | Will be specified as planning proceeds | Will be specified as planning proceeds | Will be specified as planning proceeds | 2 | -
Renovation of Labbacka tunnel | 2025 | Vuosaari–(Kerava) | 1108 | Will be specified as planning proceeds | Will be specified as planning proceeds | Will be specified as planning proceeds | 2 | -
Salo–Kupittaa: Turku One Hour Train project, Pepallonmäki tunnel work. | 2025 | (Kirkkonummi)–(Turku) | 1201 | Full service break on the Salo–Kupittaa line section for 51 days. Preliminary implementation period 2025–2027. The implementation decision has been estimated for 2024. | - | - | 2 | -
Renewal of Lammasoja railway bridge | 2025 | (Turku)–(Toijala) | 1203 | Will be specified as planning proceeds | Will be specified as planning proceeds | Will be specified as planning proceeds | 2 | -
Repair/renewal of Mustalahti underpass | 2025 | (Tampere)–(Seinäjoki) | 1302 | Will be specified as planning proceeds | Will be specified as planning proceeds | Will be specified as planning proceeds | 2 | -
Tampere deck and arena: north deck: Deck foundation and deck structure works, catenary system alterations. Minor track works. | 2025 | Tampere passenger railway yard | 1306 | Work phases in accordance with a separate plan. | - | - | 2 | VS965
Tampere deck and arena: north deck: Deck foundation and deck structure works, catenary system alterations. Minor track works. | 2026 | Tampere passenger railway yard | 1306 | Work phases in accordance with a separate plan. | - | - | 2 | VS965
Digirail: Changes in signalling equipment in the Lielahti–Pori/Rauma pilot line section | 2025 | (Lielahti)–Kokemäki–(Pori) | 1401 | Will be specified as planning proceeds | Will be specified as planning proceeds | Will be specified as planning proceeds | 1
Muurame–Jyväskylä: superstructure and substructure work | 2025 | (Tampere)–Orivesi–(Jyväskylä) | 1405 | - | Midsummer service break (preliminary). | 50–140 intermittent limits, will be specified as planning proceeds. | 1 | -
Jyväskylä–(Pieksämäki) renovation: Hankasalmi, construction of side and island platforms and renewal of the track crossing. Hankasalmi, renewal of the superstructure of r302 and r303. Hankasalmi, 4 turnout replacements. | 2026 | (Jyväskylä)–(Pieksämäki) | 1406 | Hankasalmi: 9–10 h track possessions on weekdays for two months | - | - | 1 | -
Jyväskylä–(Pieksämäki) renovation: includes an upgrade of a piece of signalling equipment, removal of level crossings, a replacement underpass, turnout replacements at Venetmäki, removal of a turnout at Naarajärvi, drainage procedures, rock cuts, areas with soft soil, bridges. | 2025 | (Jyväskylä)–(Pieksämäki) | 1406 | Hankasalmi–(Pieksämäki): 9–10 h track possessions on weekdays, 10 x 24 h and 6 x 48 h track possessions. | 1 May–30 September 2024 9–10 h track possessions on weekdays and 48 h service breaks due to a bridge transfer 1 July–30 September 2024 | 80 km/h for a leg of 10 km, within which 50 km/h for a leg of 3–5 km, and several intermittent 50 and 80 km/h limits according to a separate plan. | 1 | -
Jyväskylä–(Pieksämäki) renovation: Renewal of Tourujoki railway bridge | 2025 | (Jyväskylä)–(Pieksämäki) | 1406 | Two weeks of 9–10 h track possessions for pile driving and a 2–3 day track possession for a bridge transfer. Will prevent all traffic from Jyväskylä towards Äänekoski and Pieksämäki. | Pile driving 1–31 May Bridge transfer 1–30 September | A separate plan for speed limits. | 2 | -
Vesanka–Rautpohja: Möykynmäki tunnel excavation into a railway cutting or its renovation. | 2025 | (Haapamäki)–(Jyväskylä) | 1503 | Full service break for 11 months. | - | - | 2 | -
Painting/repair of Närpiönjoki railway bridge | 2025 | (Seinäjoki)–Kaskinen | 1506 | Will be specified as planning proceeds | Will be specified as planning proceeds | Will be specified as planning proceeds | 2 | -
Renewal of Koria overpass | 2025 | (Lahti)–(Kouvola) | 1601 | Will be specified in spring 2023. Full service break for the old bridge, speed limits for the new bridge | Will be specified in spring 2023
Repair of Tommolankatu overpass | 2025 | (Lahti)–Heinola | 1604 | Will be specified as planning proceeds | Will be specified as planning proceeds | Will be specified as planning proceeds | 2 | -
Kouvola–Pieksämäki: Repair of Venekallio, Vuohijärvi and Kulonpalonvuori tunnels | 2025 | (Kouvola)–(Pieksämäki) | 1605 | 8 h weekday service breaks 23:40–7:40 or 3:00–11:00 Sun/Mon–Thu/Fri for a period of 8 weeks. Excavation of tunnel ends will require two 24 h service breaks. | - | - | 2 | -
Imatra–Joensuu superstructure work | 2025 | (Parikkala)–(Joensuu) | 1705 | Daily 8–10 h track possessions. | - | 80/50 | 2 | -
Superstructure replacement on line sections Porokylä–Kontiomäki and Vuokatti–Lahnaslampi | 2025 | Uimaharju–Porokylä | 1708 | Daily 10 h track possessions | - | - | 2 | VS2456
Joensuu–Ilomantsi: renovation | 2025 | (Joensuu)–Ilomantsi | 1710 | Ilomantsi closed 12 September–9 October 2022. Renewal of superstructure (Tuupovaara)–Ilomantsi 2 May 2022–31 July 2022 closed to traffic Mon–Thu. Tuupovaara closed 17–28 July 2022 | - | - | 2 | -
Repair of Lestijoki railway bridge | 2025 | (Kokkola)–(Ylivieska)–(Oulu) | 1901 | Will be specified as planning proceeds | Will be specified as planning proceeds | Will be specified as planning proceeds | 2 | -
Signalling equipment work and commissioning on line section and traffic operating points related the Northern Finland’s Remote Control Project (POKA) | 2025 | Oulu | 1904 | In accordance with a separate plan. | - | - | 1 | -
Oulu railway yard improvement | 2025 | Oulu railway yard | 1906 | Changes in track access. For example, car-carrier wagon loading is prevented for a couple of months. | - | - | 2 | VS2325
Repair of Petiäisenkoski railway bridge | 2025 | (Iisalmi)–(Kontiomäki) | 2101 | Will be specified as planning proceeds | Will be specified as planning proceeds | Will be specified as planning proceeds | 2 | -
Repair/renewal of Kemijoki arterial railway’s railway bridge | 2025 | (Isokylä)–Kelloselkä border | 2205 | Will be specified as planning proceeds | Will be specified as planning proceeds | Will be specified as planning proceeds | 2 | -