## Slide 1
Lielahti–Kokemäki project alliance Outcomes
Mikko A. Heiskanen, Finnish Transport Agency
19.5.2015

## Slide 2: Lielahti-Kokemäki project alliance
First public sector project alliance in Europe
Renovation of TamperePori railway, ca. 90 km
Project developement phase and construction phase were executed in less than four years (August 2011–February 2015)
Alliance participants
  Owner participant: Finnish Transport Agency
  Non-owner participant: VR Track
The alliance was responsible for executing all sectors of the project
Total budget of the project is 106,4 M€, which includes
  costs for procurement phase, development phase and delivery phase including materials supplied by the owner
  costs for guarantee period (5 years)
Total budget was set in May 2011, and it includes all the cost level changes of the project and risks

## Slide 3: Efficient lead time
1.6.2012
13.2.2015
2020
1.4.2011
STRATEGY
CONSTRUCTION
GUARANTEE PERIOD
Present
13.8.2011
PROJECT
DEVELOPEMENT PHASE
PROJECT DELIVERY PHASE
FORMING THE ALLIANCE

## Slide 4: Efficient decision making
ALLIANCE LEADERSHIP TEAM (ALT)
CONSTRUCTION TEAM
SPECIALISTS AND CONSTULTANTS
WORKSHOP TEAMS
PLANNING
CONSTRUCTION
ALLIANCE MANAGEMENT TEAM (AMT)
4
19.5.2015

## Slide 5: Collaboration in project management
Traditional procurement
2011
2012
2013
2014
2015
2016
2017
2018
Project schedule
Railway plans
Construction plans
Construction
Commissioning
2011
2012
2013
2014
2015
2016
2017
2018
Alliance procurement
Total lead time of the project has shortened ca. 2 years
Project schedule
Railway plans
Construction plans
Construction
Commissioning

## Slide 6: Collaboration between planning and construction

## Slide 7: Renewing the track superstructure

## Slide 8: Cleaning the ballast (90 km) and frost insulation (27 km)

## Slide 9: Electricity and signalling works

## Slide 10: New railway bridges
Putajanjoki bridge before
  …and after
Siuronkoski bridge before
  …and after

## Slide 11: Level crossings
Kokemäki
Vammala
Karkku
Nokia
17 upgraded level crossings
11 removed level crossings
Ahvenus
Äetsä
Heinoo
Suoniemi
Siuro
Kalkku
Lielahti
4 upgraded level crossings with new boom barriers
Significant improvements in both road traffic safety and railroad safety

## Slide 12: Expanding a rock cutting 20 000 m³

## Slide 13: Common goals
Indicator | Poor performace | Minimum conditions of satisfaction | Outstanding performance | KRA results | KRA score
Passenger train punctuality [%] | 70 | 85-90 | 98 | 99,65 | 26
Freight train punctuality [%] | 70 | 85-90 | 98 | 99,93 | 9
Project completion date | 31.5.2016 | 31.5.2015 | 28.2.2015 | 28.2.2015 | 20
Railroad safety defects | 25 | 6-10 | 0 | 2,5 | 5
Worksite safety level [%] | 75 | 93 | 100 | 95,8 | 7
Accident frequency | 100 | 18 | 0 | 6,2 | 12
Tot. 79
0
+100
79
-100
Value for money

## Slide 14: Usability of the railway during the alliance
27 000 trains passed the project area during three years of construction. Only 42 of these were late or cancelled because of the construction works.
Punctuality of the train traffic considering the effect of the construction works:
Freight traffic
99,93%
Passenger traffic
99,65%
Coordination between rail traffic and the construction works has been excellent

## Slide 15: Safety as a key result area
Safety has been on very high level throughout the project
Alliance has been able to create processes for safety, that work as a natural part of everyday work
A total of 12 000 notes on weekly safety level measurings
Safety level at the work site 95,8%
Total hours of work: 640 000 h
4 accidents, in which only 19 man-days were lost
Accident frequency 6,2
3 railroad safety defects:
  Communication between the worksite and traffic control
  Securing the road traffic at level crossing
  Working in safety device premises without a permission
  Railroad safety on a good level

## Slide 16: Outcomes of the commercial model
Palveluntuottajan
korvattavat
kustannukset
Projektikohtaiset
yhteiskustannukset
Palkkio korvattaville
kustannuksille
Project costs
71,5 M€
Actual outturn cost prediction at the end of the construction period: 80,0 M€
Owner has increased the project
scope with 4,2 M€ gained during
the alliance
Forecast:
Gain +7,0 M€
Direct project costs
for non-owner
participant
Owner´s costs
Fee for project
specific costs
Risks
Goals are achieved and the success of the project can be well demonstrated
12%/25,6%

## Slide 17: Positive publicity is part of the success

## Slide 18: Work site of the year in 2012 !

## Slide 19: IPD-Projects in Finland: 23 projects, total worth of 1,2 billion €
Source: Vison Alliance Partners Oy, Lauri Merikalliio

## Slide 20: More information on the project:
Alliance project manager:
Mikko Nyhä, VR Track p. 040 863 0450 mikko.nyha@vr.fi
Mikko A. Heiskanen, FTA
p. 029 534 3808
mikko.heiskanen@liikennevirasto.fi
liikennevirasto.fi/lielahti-kokemaki